## 1 – Risk Assessment
|  | Balloon Release Risk Assessment |  |  |  |  | Version | 1.1
[7 empty] | Release Date | 23 May 2022
[7 empty] | Approved By | Lewis McCluskey
[7 empty] | Next Review | 1 April 2023
Risk No. | Description of Hazard | Description of Risk | Consequence | Likelihood | Consequence | Risk Level | Risk Treatment Strategy |  | Residual Likelihood | Residual Consequence | Residual Risk
1 | Balloon flying in airspace where aircraft might be operating | Single-engine light aircraft, glider or consumer drone strikes a "Light Balloon" as per Subpart 101.E (150g payload slung under a 600g balloon) | Aircaft may suffer mechanical damage or impairment of propulsion or controllability leading to forced landing or disruption of intended flight operations | 2 | 1 | 3 | - NOTAM - Visual check prior to release - Warnings transmited from ground based VHF radio on the Ceduna CTAF frequency if any aircraft are visible or audible - Balloons and payloads sourced from experienced international supplier (Vaisala) - On-range surveillance of aircraft using Flight Explorer may be employed |  | 1 | 1 | 2
2 |  | Multiple engine propeller aircraft strikes a "Light Balloon" as per Subpart 101.E (150g payload slung under a 600g balloon) | Aircaft may suffer mechanical damage or impairment of propulsion or controllability leading to forced landing or disruption of intended flight operations | 2 | 1 | 3 | - NOTAM - Visual check prior to release - Warnings transmited from ground based VHF radio on the Ceduna CTAF frequency if any aircraft are visible or audible - Balloons and payloads sourced from experienced international supplier (Vaisala) - On-range surveillance of aircraft using Flight Explorer may be employed |  | 1 | 1 | 2
3 |  | Jet aircraft strikes a "Light Balloon" as per Subpart 101.E (150g payload slung under a 600g balloon) | Some potential for disruption or disturbance to airspace user if they strike balloon or see one in close proximity potentially leading to disruption of intended flight operations | 2 | 1 | 3 | - NOTAM - Visual check prior to release - Balloons and payloads sourced from experienced international supplier (Vaisala) |  | 1 | 1 | 2
4 | Pilots failing to read NOTAMs | Pilots not maintaining watch for balloons in area | Aircraft may suffer mechanical damage or impairment of propulsion or controllability leading to forced landing or disruption of intended flight operations | 2 | 1 | 3 | - Information distributed directly to known operators in advance of launch campaign notifying them of the balloon release period and that NOTAMs will be promulgated. - On-range surveillance of aircraft using Flight Explorer may be employed - Warnings transmited from ground based VHF radio on the Ceduna CTAF frequency if any aircraft are visible or audible - Balloons and payloads sourced from experienced international supplier (Vaisala) |  | 1 | 1 | 2
5 | Balloons released at night | Pilots unable to visually spot a balloon which results in collision with a "Light Balloon" as per Subpart 101.E (150g payload slung under a 600g balloon) | Aircraft may suffer mechanical damage or impairment of propulsion or controllability leading to forced landing or disruption of intended flight operations | 2 | 1 | 3 | - NOTAM - Visual check prior to release - Warnings transmited from ground based VHF radio on the Ceduna CTAF frequency if any aircraft are visible or audible - Balloons and payloads sourced from experienced international supplier (Vaisala) - On-range surveillance of aircraft using Flight Explorer may be employed |  | 1 | 1 | 2
6 | Loss of radiosonde tracking | Launcher is unable to comply with requests from ATC to know the location of a balloon. | ATC face difficulty or delay in coordinating local aircraft in an emergency situation. | 2 | 1 | 3 | - Should a radiosonde fail to transmit and cannot be tracked via UHF receiver or SondeHub, Launcher may attempt to predict the real time flight path based on its simulation tool with forecast data provided by the Bureau of Meteorology or Spire. - Balloons and payloads sourced from experienced international supplier (Vaisala) |  | 1 | 1 | 2
7 | Failure of ground based VHF radio | Launcher is unable to transmit radio warnings on the Ceduna CTAF frequency. Pilots relying on VHF for safety information subsequently proceeds into the flight path of the balloon where collision occurs. | Aircraft may suffer mechanical damage or impairment of propulsion or controllability leading to forced landing or disruption of intended flight operations | 2 | 1 | 3 | - Launcher maintains a backup VHF radio on range - NOTAM - On-range surveillance of aircraft using Flight Explorer may be employed - Visual check prior to release |  | 1 | 1 | 2

## 3 – CASA Criteria Lookup
|  | 1 | 2 | 3 | 4 | 5
|  | Negligible | Minor | Moderate | Major | Severe
5 | Almost Certain | 6 | 7 | 8 | 9 | 10
4 | Likely | 5 | 6 | 7 | 8 | 9
3 | Possible | 4 | 5 | 6 | 7 | 8
2 | Unlikely | 3 | 4 | 5 | 6 | 7
1 | Rare | 2 | 3 | 4 | 5 | 6
>8 | Extreme Risk | Detailed treatment plan and constant monitoring required
2019-06-07 | High Risk | Requires high level treatment and monitoring
2019-04-05 | Medium Risk | Requires moderate planning and monitoring as appropriate
<3 | Low Risk | Managed by normal operational procedures

## 2 – Background Information
Risk Assessment Guidelines
A Risk Assessment should not only be viewed as being a requirement for applications but also as a practical approach to systematically reducing risks.
By conducting a thorough Risk Assessment, the procedures for operating within the conditions of the Approvals are taken into account during the planning process. The risk reduction strategies (risk mitigators) that form part of the risk assessment process may assist in the development of standard operating procedures for all ongoing operations. Additional benefits may also be gained when the risk assessment is used as a reference document and integral part of the induction and training of new Club Members.
The Risk Assessment Plan should be viewed as a quality control document with a focus on risks and as such, should be treated as a “living document” that is reviewed and updated periodically.
An appropriate starting point in the development of a risk assessment is defining the terms that are used; a Glossary of Terms. An understanding of these terms is required to successfully build the risk assessment;
Hazard – anything that may cause harm to people, or damage to aircraft, equipment or structures. (A piece of equipment, a process, situation or practice)
Risk – the possibility that something may occur due to exposure to the Hazard; this is often measured in terms of Likelihood and Consequence.
Likelihood – a description of the probability that the Risk may occur. (eg. 5-10% chance that the risk may occur)
Consequence – the outcome of an event. (eg. Non-compliance to Regulations or Approval. Mid-Air collision, injury to spectators.)
To assist in better understanding of these terms, the following examples show the relationship between Hazard, Risk and Consequence;
1. Hazard – Airspace incursion. Risk – Collision between model and manned aircraft. Consequence – Damage to both of the aircraft with possible subsequent crash of manned aircraft leading to possible injury or death of aircraft occupants.
2. Hazard – Mechanical. Risk – Failure of Engine. Consequence – Aircraft not able to return to land at the Aerodrome and consequently lands in an inappropriate area resulting in damage to aircraft and possible injuries to spectators.
3. Hazard – Radio failure. Risk – Lack of ability to monitor airspace using radio. Consequence – Heightened possible risk of collision between model and manned aircraft in certain airspace.
The Risk Assessment should include presentation of all of the following information;
1. The Risks (identified by asking “What can go wrong?”) in conjunction with the Consequences of those Risks – this information is tabulated and given a Risk Rating/Level (Likelihood + Consequence). It is important that this step is done before treatment of the identified risks.
2. The Risk Treatment strategy is a method of reducing the risk (eg. Additional Airband VHF Radio available as a backup). A subsequent risk rating should also be evaluated after implementation of the risk reduction strategy.
It is the information presented in the Risk Assessment that is used by CASA to assess all Applications for approvals, permissions or exemptions.
To assist further, attached is an example of the format and presentation of the required information. Please Note: There are other Risk Assessment formats that are acceptable, the example provided utilises the CASA Risk Assessment Format.
The CASA Risk Assessment spreadsheet file is enabled to automatically calculate the Risk Levels (to ensure accuracy) with the risk colour rating (green, yellow, orange or red) automatically changing in response to relevant risk levels calculated.
Presenting the risks and the treatment strategies that you have identified in a familiar format, assists CASA to effectively make an assessment and evaluate your application for an approval or exemption from the regulations. Given that CASA regulations are in place to mitigate risk in many aviation operating environments, a substantial safety case is required to provide CASA with assurance that the operations being applied for, are able to be conducted within acceptable risk levels.
Please note; as the consequence of a particular situation does not change, it is not generally possible to reduce the Consequence of hazards. (eg. Model aircraft collision with a manned aircraft will always have the same possible consequence of injury/death irrespective of the risk mitigators employed.) In this situation it is more likely that the mitigating strategy will only reduce the Likelihood of an aircraft crash. By reducing the likelihood the overall residual risk can still be reduced.
Risk Treatment Strategies
The standard approach to treatment of risk is by utilising the “Hierarchy of Control” method. This simple procedure assists in devising the most effective risk mitigation strategy for the hazards identified.
The Hierarchy of Control method provides a framework for identifying the most effective and appropriate method of dealing with the known hazards. Ranking the possible risk treatment strategies from elimination of the hazard through to minimising the exposure to the hazard allows the most appropriate method of control to be identified and assessed.
It is more appropriate to deal with the hazards at the upper level of the Hierarchy of Control, however, sometimes it is not possible to use the highest level of control and therefore a lower level of control must be implemented.
Hierarchy of Control processes;
1. Eliminate Hazard – Remove the Hazard completely (eg. Hazard – Loss of control of model. Control – Unable to eliminate this Hazard.)
2. Substitute – Find a substitute to deal with the Hazard directly – (eg. Hazard – Loss of control of model. Control – Use a Control Line model for the display.)
3. Engineer a control method – Find a solution that requires some modification to the equipment used (eg. Hazard – Loss of control of model. Control – Only use equipment that has a failsafe on servos.)
4. Administer the Hazard – Provide Training and Education or signage to ensure knowledge of the Hazard and to reduce the Risk (eg. Hazard – Loss of control of model. Control – Flight done in accordance with Standard Operational Procedures; Ensure no inflight turns are done towards spectators. Models in flight should remain clear of the built up areas with no flight paths taken towards built up areas.)
5. Personal Protection Equipment (PPE) – Use safety clothing and other protection equipment to reduce the consequences of the Hazard (eg. Hazard – Loss of control of model. Control – Unable to use PPE methods to control Risks)
During the Risk Assessment process it is beneficial to examine possible preventative mitigation strategies as well as the operational response required should a hazard present itself during flight. For example;
VHF Radio failure Prevention – how might a radio failure be prevented? (Preventative maintenance, logging/reporting system for any radio issues noticed, appropriate pre-flight radio checks, systematic renewal of radio batteries etc.)
VHF Radio failure Procedures – use of a Warning Siren to alert all pilots to the radio failure. Subsequent action by pilots is to limit flight to below 400’ AGL until further notice.
The mitigation of risks involved in model flying displays will allow the Organiser and Display Director to be assured that the display will not present any exceptional risk to themselves (as the persons being responsible for all aspects of the display), the model aircraft operators involved or the spectators of the event.
How low does the Risk Factor need to be?
ALARP – (as low as reasonably practicable), means all efforts should be made to reduce risks to the lowest level possible until a point is reached where any further risk reduction (by additional mitigation strategies) is either a waste of resources or the risk has reached an acceptable level. The acronym ALARP depicts the notion that in aviation safety, risks cannot be completely eliminated, however they may be reduced to a level that is either tolerable or broadly acceptable.
In some instances the Risk Factor after mitigation may still be in the High region but may be considered ALARP.
An example of this could be;
Hazard – Aircraft propellers on electric powered model aircraft.
Risk - Personal injury to controller’s hands (due to propellers) if control unit is not switched off prior to retrieving model aircraft after landing.
Mitigation – Propeller guards on all electric powered model aircraft.
Review – The cost involved in conversion of all electric powered models to include a propeller guard would be exceedingly high. The historical incident data suggests that there has only been one instance of a controller being injured during operations in the preceding 3 years. Due to the costs involved and the acceptance by the industry of the risk, the risk is deemed to be ALARP.
CASA places heightened importance on the protection of other airspace users and members of the general public not associated with the operation of the model as the highest priorities in assessing these applications, however the risk posed to model aircraft operators as informed participants must also be given due consideration.
Should you require any further information in relation to Model Aircraft Approval applications, please contact sport@casa.gov.au